DVPR

1. 01_dvpr_introduction

- Stehen alle Infos drin, Bücher, …

2. 02_pm_introduction

- What is a project?

  - A project is a temporary endeavor undertaken to create a unique product, service or result

  - Why? To sustain business

  - Duration? End when objectives are reached or project is terminated

  - Size? Large or small, short or long, doesn’t mater

- Project Management: application of knowledge, skills, tools and techniques to project activities to meet project requirements

- Project is a success when:

  - Met Scope/Quality, Time and Cost goals

  - Satisfied the customer/sponsor

  - Project met its main objective

- Role of Project Manager:

  - Responsible of planning, scheduling, coordinating and working with people to achieve project goals

  - 97% of successful project were led by experienced project managers

- Skills a Project Manager need:

  - Body of Knowledge (knows what a project is and what he has to do)

  - Application area knowledge, standards and regulations

  - Environment knowledge

  - General management knowledge and skills

  - Soft skills

- What helps a project to succeed: user involvement, executive support, clear business objectives, emotional maturity, optimizing scope, agile process, project management expertise, skilled resources, execution, tools and infrastructure

- Program Management:

  - Program is a group of related projects managed in a coordinated way to obtain benefits and control not available from managing them individually

  - Program manager manages project managers

  - Program example:

- Project Portfolio Management:

  - Organizations group and manage project and programs as a portfolio of investments that contribute to entire enterprise’s success

  - Portfolio managers help organizations make wise investment decisions

3. 03_pm_basics

- Project: think, do, close (think before you act)

- 4 major anchor points to manage a project:

- Scope:

  - Well-defined project scope is a necessity to ensure the success of the project

  - Clear vision, agreement on the outcome of the project

- How to successfully define a scope:

  - Identify the project needs

  - Confirm the objectives and goals of the project

  - Clear project scope description

  - Exceptions and acceptance

  - Identify constraints

  - Identify necessary changes

- Quality:

  - Means meeting the needs of customers (“fit for use”)

  - Can be checked by testing based on mutual approved test requirements by developer, user and project owner

- Time & Planning:

  - Think – Agree – Do/Act – Check – Deploy – Close

  - Planning must be continuous throughout the project, no plan can or should survive in its original form from the start of the project to the finish

- Money / Cost Management:

  - Process of estimating, allocating and controlling the costs

  - Allows to predict coming expenses in order to reduce the chances of it going over the budget

- 4 points are in “Project Devils Square”

- Need to:

  - Project organization to run the project (Demand, Supply, Project Owner)

  - Communication

  - Manage risks and issues

  - Manage changes

4. 04_pm_basics_2

- Work Breakdown Structure (WBS):

  - Is a deliverable-oriented hierarchical decomposition of the work to be executed by the project team to accomplish the project objectives and create the required deliverables

  - Organizes and defines the total scope

  - Decomposed into work packages

- Product Breakdown Structure (PBS):

  - Tool for analyzing, documenting and communicating the outcomes of a project, forms part of product-based planning

- Complementary: PBS  WBS

  - PBS is identical in format of WBS, but is a separate entity, is used at a different step in planning process

  - PBS precedes the WBS and focuses on cataloguing all the desired outputs needed to achieve goal, feeds into creation of WBS, identifies the task and activities required

  - In a nutshell: PBS defines where you want to go, WBS tells you how to get there

- Example: breakdown of mountain bike

  - PBS:

  - WBS:

- Presentation then tells how to create a PBS / WBS diagram

- Quality review technique:

  - Structured procedure designed to access whether a deliverable is ‘fit for purpose’ or conforms to requirements

  - Can be invoked at any point during project

5. 05_pm_methods_and_tools

- RICAD – Logging of what is happening

  - Risks

  - Issues

  - Changes

  - Actions

  - Decisions

- Risks:

  - Set of events that will have an effect on achieving the project goals

  - Uncertain event will have a positive or negative effect on project

  - Risk Log provides a record of identified risks relating to project, including status and history. Used to capture and maintain information on all the identified threats and opportunities

- Issues:

  - Term used to cover any concern, query, request for change, suggestion or off-specification raised during the project

  - Issue Log capture and maintain information of all issues being formally managed, monitored by Project Manager

- Risks can be monitored by a Probability/Impact Matrix

- Changes:

  - Scope control is process of managing the scope of project when changes happen, need to set up change control process

  - When changes are uncontrolled, it’s a scope creep

  - Change management is important. Project Manager must examine proposed change and determine effect on project

  - Changes can be anything (Scope, Quality, Timelines, Money)

  - Captured in Change log

- Decisions:

  - Captured in decision log

  - Must be captured to avoid later discussions / scope creeps

6. 06_pm_planning

- Importance of Project Schedules:

  - Managers want project finishing on time

  - Time has least amount of flexibility, passes no matter what happens

  - Schedule issues are main reason for conflicts

- Project Time Management Process:

  - Planning schedule management: policies, procedures and documentation for planning, executing and controlling

  - Defining activities: specific activities to produce project deliverables

  - Sequencing activities: identifying and documenting the relationships between project activities

  - Estimating activity resources

  - Estimating activity durations

  - Developing the schedule: analyzing activity sequences, activity resource estimates and activity duration estimates to create the project schedule

  - Controlling the schedule: controlling and managing changes to project schedule

7. 08_agile_principles_and_mindset

- Agile Project Management: iterative development methodology that values human communication and feedback, adapting to changes and producing working results

- Why agile?

  - Different projects – different methods

  - Better in complex projects with fast-moving environments

- “Normal” project vs. Agile project:

- Advantages of agile:

  - Increase ROI (return of invest): continuous flow and focus

  - Deliver reliable results: engage customers

  - Expect uncertainty: manage with iterations and adaption

  - Unleash creativity and innovation: individuals make the difference

  - Boost performance: accountability for results

  - Improve effectiveness: practices, processes, strategies

- Agile Triangle:

- Agile Manifesto:

  - Individuals and interactions over processes and tools

  - Working software over comprehensive documentation

  - Customer collaboration over contract negotiation

  - Responding to change over following a plan

- Agile Methodologies:

  - Scrum

  - Extreme Programming (XP)

  - Lean Product Development

  - Kanban

  - Feature-Driven Development

- Scrum

- Three pillars:

  - Transparency

  - Inspection

  - Adaption

- Scrum overview:

- Sprint:

  - Timeboxed 1-4 weeks (most 2 weeks)

  - Mini project

  - Scope defined at beginning

  - Work will be done based on items on sprint backlog

- Scrum Roles:

  - Product Owner (demand): Product backlog, Business Value, Contact person for team (i.e., the customer)

  - Development Team (supply): Estimations, Delivers releasable increments, Interdisciplinary, Self-organizing

  - Scrum Master (service): Ensures process, Helps removing impediments, Moderation, Coaching

- Product Owner:

  - Product Owner responsible for maximizing the value of the product and work of the Development Team

  - Responsible for managing Product Backlog

- Product Backlog:

  - List of everything which might be needed for the product (Backlog Items)

  - Single source of requirements

  - Product Owner puts new Backlog Items into Product Backlog

  - Order of Product Backlog defines “importance” and thus steers which one to do next

- Sprint Planning Meeting:

  - Participants: Scrum Master, Product Owner, Development Team

  - Timeboxed: 2 hours per 1 week sprint

  - Scrum Master teaches how to stay in timebox

  - Goals: which work to complete in the next sprint and how?

  - Team decides based on capacity and velocity how much work can be done until end of next sprint

  - Outcome: Sprint Goal and Sprint Backlog

- Daily Meeting:

  - No Management reporting meeting

  - Timebox: 15 minutes

  - Questions: What did I do, what will I do, are there any Issues

  - No detailed discussions

  - Team getting informed about progress

- Review Meeting:

  - Participants: Scrum Master, Product Owner, Development Team

  - Timebox: 1 hour per 1 week

  - Team demonstrates results

  - Product Owner accepts or not accepts results

  - Probably new product Backlog Item occur

- Sprint Retrospective Meeting:

  - Most important Meeting

  - What went wright / wrong

  - Inspect and Adapt

  - Plan improvements

  - Scrum Master moderates

- Extreme Programming

- Core Values:

  - Simplicity

  - Communication

  - Feedback

  - Courage

  - Respect

- XP Roles:

  - Coach: similar to Scrum Master

  - Customer: Similar to Product Owner

  - Programmer: write and implement code

  - Testers: help customer to define acceptable tests

- Lean Product Development:

  - Eliminate waste

  - Empower the team

  - Deliver fast

  - Optimize the whole

  - Build quality in

  - Defer decisions

  - Amplify learning

- Kanban: Signboard to visualize workflow

- Feature-Driven Development (FDD)

  - First building an overall model

  - Build a feature list, plan the work

  - Design and build features

8. 09_agile_value_driven_delivery

- Reason project exist is to generate business value

- Value Driven Delivery: focus on delivering value

- “Which choice will add the most value for the customer?”

- Aim to deliver highest value portions of the product ASAP (Eat your dessert first)

- Minimize waste:

  - Unclear requirements

  - Partially done work

  - Extra processes

  - Extra features

  - Task switching

  - Waiting

  - Defects

- Financial Assessment Metrics:

  - Return of Investment (ROI): ratio of the benefits from an investment to the money invested in it, higher equals better

  - Net Present Value (NPV): present value of a revenue stream (income minus costs), higher equals better

  - Internal Rate of Return (IRR): discount rate at which the project inflows and outflows are equal, higher equals better

  - Earned Value Management (EVM): measuring the cost, scope and time performance by comparing planned value, estimated costs with actual costs and earned value

- Multiple Prioritization Schemas:

  - Simple: Prio 1, Prio 2, Prio 3

  - MoSCoW: Must have, Should have, Could have, Would like to have, but not this time

  - 100 Point Method: each stakeholder has 100 Points to vote for the most important requirements

- Minimal Viable Product (MVP)

  - Package of functionality that is complete enough to be useful, but not represent the whole project

- Verifying and Validating Value

  - Validation: Are we building the right product?

  - Verification: Are we building the product, right?

  - Communication is important

9. 10_agile_stakeholder_engagement

- Principles of Stakeholder Engagement

  - Get the right stakeholders / stakeholder analysis

  - Cement stakeholder involvement

  - Actively manage stakeholder interest

  - Frequently discuss what “done” looks like

  - Show progress and capabilities

  - Candidly discuss estimates and projections

10. 12_agile_adaptive_planning

- Timeboxing: fixed cost and timeframe

- Decomposing requirements:

  - Work that cannot be accurately sized, estimated and planned  need to decompose or break down

- User Stories:

  - short, simple description of a feature, from the perspective of the person who desires the new capability

  - Small chunks of business functionality within a feature

  - Agile teams break down work into user stories

  - Will be put on the prioritized product backlog

  - Format: As a <type of user>, I want <goal> so that <reason>.

- User stories should follow INVEST acronym:

  - Independent

  - Negotiable

  - Valuable

  - Estimable

  - Small

  - Testable

- Story points:

  - Team should own the definition of their story points

  - Story points estimates should be all-inclusive

  - When aggregating estimates, the totals do not need to match

  - Complexity, work effort and risk should be included in estimates

11. 13_agile_problem_detection_and_resolution

- Technical debt

  - Backlog of work that is caused by not doing regular clean-up, maintenance and standardization

  - Backlog od things that should be done to make things easier

  - Solution: Refactoring

- Detecting problems: Lead Time and Cycle Time

- Lead Time:

  - How long something takes to go through the entire process, e.g., from design to shipping

  - Is a tool to identify and diagnose problems

- Cycle Time:

  - Subset of Lead Time

  - How long does something take through part of the process, e.g., from coding to testing

- Cycle Time = WIP / Throughput

  - WIP = Work in progress

  - Throughput = amount of work that can be processed through a system in a given amount of time (what was done in an iteration)

- Variance Analysis: accept variance or take action?

- Best practice:

  - Do not micromanage, most variances are quite ok and normal

  - Look for external triggers

  - Decide: is it a common cause  take no action; is it a special cause (e.g., external trigger)  take action

12. 14_agile_continuous_improvement

- Kaizen: Japanese process for continuous improvement, means “change for better”

- Basis for agile way of making small improvements on a daily base

- Focuses on encouraging the team frequently and implement small incremental improvements

- It is a principle, not a standardized framework

- Kaizen key to-do’s:

  - Improve the quality of your products / processes

  - Review the cost live cycle

  - Improve efficiency and productivity

  - Use training to develop people

  - Lead people to their best

  - Break down barriers

  - Give people autonomy & responsibility

- PDCA – Cycle: four-step model for carrying out change

- No end, should be repeated over again  continuous improvement

- Procedure:

  - Plan: recognize an opportunity and plan a change

  - Do: test the change

  - Check: review the test, analyze the results and identify what you have learned

  - Act: take action based on what you learned

- If change did not work, go through cycle again to test something new

- If successful, apply it, write down findings, begin cycle again

- Process Tailoring: tailor a process to the current needs

- Not creating a completely new process, only tailor parts of it

- Changes must be documented

- Can boost flexibility and speed

- Risks:

  - Takes time

  - Can get out of hand

  - Experience is needed

- Fail Fat / Fail Forward (Learn by Doing): Do not waste too much time on lesson lend, document failures and quickly continue

- Continuous learning experience

- Adapt yourself, do not make same mistakes over again

- Individual process

- Perpetual beta (“banana principle”): buy the product before it reaches the final state

- Development continues after purchase

- Customer finances the product

- Most common in software industry

- Alpha-/Beta-version of software application

- Six Sigma: management toll for process optimization

- DMAIC Cycle:

  - Define: identify processes which could be optimized

  - Measure: measure how the process performs until now

  - Analyze: analyze why the process is executed in its current state

  - Improve: try to find improvements which could optimize the process

  - Control & Implement: Control the new process and evaluate the impact of the change concerning to price / quality / time

- Project Pre-Mortems: exercise that aims to identify possible failure points on a project before they happen so that we can avoid or minimize those risks

  - Especially valuable on long-running projects, because more changes can happen

- Retrospective: what worked well, what did not work well, what action can we take to improve our process going forward

- 5 steps:

  - Set the stage: to eliminate awkwardness in team, set stage as a game to make people comfortable

  - Gather data: capture information from last sprint, wins and failures

  - Generate insight: get more insight in information and work on possible solutions

  - Decide what to do: create action items to work on

  - Close retrospective